# Ministry of Education, Culture and Research (MoECR)

# Moldova Higher Education Project (MHEP)

Procurement References: MD-MOED-205737-CS-INDV

TERMS OF REFERENCE

Individual Consultant to provide support to the Ministry of Education, Culture and Research in developing of the Terms of Reference for digitalization of archive of degree documents (diplomas)

      - Background information on the project

Moldova Higher Education Project (MHEP) is a World Bank (hereinafter “the Bank”) - financed Project to be implemented between May 2020 and December 2025.

The total cost of credit is EUR 35.7 million (US$39.4 million equivalent) financed by the International Development Association (IDA) and is provided to the Republic of Moldova in support of Moldova Higher Education.

The Project Development Objective is to improve the labor market orientation of selected higher education institutions and the quality assurance mechanisms. The Project is organized around three components and includes systemic interventions in the areas of higher education quality, financing and management, as well as a targeted program to be implemented by selected higher education institutions and pedagogical colleges to address some of their most pressing needs in labor market orientation.

The MHEP components are described below:

- Improving the Quality Assurance Mechanisms

- Improving the Labor Market Orientation through Targeted Interventions

- Project Management

Component 1 – Improving the Quality Assurance Mechanisms. This component aims to improve Moldova higher education system’s quality assurance mechanisms, which would also contribute to improve its labor market orientation. It comprises three sub-components that support activities in: (i) National Qualifications Framework (NQF) and Quality Assurance (QA); (ii) System Management and Monitoring; (iii) Higher Education Financing.

Component 2 – Improving the Labor Market Orientation through Targeted Interventions. This component will finance the design and implementation of a targeted and needs-based program (Higher Education Improvement Program - HEIP) aimed at improving the labor market orientation of Moldova’s higher education institutions, as well as their research capacity.

Component 3 – Project Management. This component will support the day-to-day management of the Project by the MoECR with assistance of a dedicated team of individual consultants who would provide managerial, fiduciary, and technical support to the implementation of the proposed Project for its full duration.

Component 1 of the Project will finance relevant activities in higher education quality assurance, including the Digitalization of the archive of degree documents (diplomas) that were issued until 2008. This activity will be implemented by the Information and Communication Technologies Center for Education in close collaboration with the MoECR.

      - Objective of the assignment

The consultant will develop the Terms of Reference (ToR) for Digitization of the archives of the registries of degree documents that have been issued by national education institutions (ISCE levels 3 – 8) starting from 1970 and until 2008.

      - Scope of Work

The assignment includes but is not limited to reviewing national legislation relevant to archiving and digital archives storage processes, interviewing educational institutions and elaboration of the detailed ToR that will be incorporated in the Bidding Documents according to the Bank procedures (ICB for Information Systems).

For all key activities and deliverables, the consultant will perform the following tasks:

- Collect data on the state of the archives of the registries of degree documents in all types of educational institutions at ISCE levels 3 – 8 (gymnasiums, high schools, professional schools, colleges, universities):

  - conduct selective visits to archives of educational institutions. Estimated number of institutions is up to 25 up to 5 institutions from each ISCED level 3-8;

  - development of questionnaires regarding the archives state and analysis of the questionnaires results;

  - analysis of the collected information and estimation of workload for digitization of the archives of degree documents registers.

- Review of the national legal framework regarding the archives of educational institutions and elaboration of proposals for its modification / completion, including elaboration of draft normative documents that would ensure, if necessary, the process of digitization and proper storage (security and confidentiality) of digital archives of degree documents.

- Development of the ToR for digitization of the registries of degree documents archives including the requirements for the digitization process as follows:

  - description of the process and steps to be followed;

  - description of the list of documents to be digitized;

  - description of the metadata for each type of document;

  - description of the logistics of the digitization process and accompanying documentation requirements.

  - description of security measures to set up and followed;

- Development of requirements for the digitization software and subsequent use of digitized data:

  - database structures for storing the digitized registries of degree documentss;

  - basic rules for data processingin the state language and other languages such as Russian, Ukrainian, Bulgarian and Gagauzian, including those in Cyrillic script (issued until 1990);

  - the main functionality of entering, updating, searching and presenting information from digitized degree documents registries.

5. Development of a draft timetable for the digitization of the archives of degree documents registries and recommendation for the company qualification requirements.

      - Duration of the assignment, estimated time input and expected outcomes

This consultancy is expected to last 3 months starting in July 2021, with the deliverables submitted electronically as following:

| Deliverables | Submission Deadline | Approved by |
| --- | --- | --- |
| 1. Report regarding the state of the archives of the degree documents registries (in Romanian) | 2 weeks from signing the contract | MoECR |
| 2. List of proposed changes in the legal framework (in Romanian) | 4 weeks from signing the contract | MoECR |
| 3. Drafts of normative documents on the organization of the process of the digitalization of the diploma archives and their storage (in Romanian). | 8 weeks from signing the contract | MoECR |
| 4. ToR for the digitalization of the archives of the degree documents registers, including the proposed timetable for digitalization process (in Romanian and English). | 14 weeks from signing the contract | MoECR |

      - Qualification requirements and evaluation criteria

- General experience (30 points):

- At least university degree in areas such as computer sciences, economics, business administration, public administration, engineering, telecommunications or related areas;

- At least 3 years of professional experience in IT area;

- Proven track record of similar assignments (min. 2 assignments).

- Adequacy for assignment (50 points):

- Experience in processes systematizing and data systematization. The experience in analysis and design of digitizing archives would be an asset;

- Experience in similar complexity assignments;

- Participation in the elaboration of the regulatory documents in ICT field would be an asset;

- Working experience in education system policies would be an asset.

- Languages and Communication (20 points):

  - Written and verbal communication skills;

  - Flexibility and good analytical skills;

  - Very good teamwork skills;

  - Excellent knowledge of Romanian (both written and oral),

  - Good knowledge of Russian would be an asset;

  - Good knowledge of English and ability to develop technical documents in English.

      - Institutional Arrangements

The Consultant will report to the Project Coordinator, Project Executive Director, MoECR's ICT Department and Head of the Information and Communication Technologies Center for Education. The Project team and Department of National Qualifications Framework within MoECR will oversee the process of consulting services and will manage the contract implementation.

The MoECR and Project team will provide the Consultant the necessary support to complete the assignment: documents necessary for assignment accomplishment and necessary work conditions.

Confidentiality statement: All data and information received from MoECR for the purpose of this assignment is to be treated confidentially and are only to be used in connection with the execution of these Terms of Reference. All intellectual property rights arising from the execution of these Terms of Reference are assigned to MoECR. The contents of written materials obtained and used in this assignment may not be disclosed to any third parties without the expressed advance written authorization of the MoECR.